## Detailed Plan
Digitalized Practicum Completion System - Project Timeline
WBS Number |  | Task Name/Title | Assigned To | Planned Start Date | Planned End Date | Deadline | Progress (%) | Duration (hours) | Status | Priority | Task Description | Cost/Efforts | Actual Cost/Efforts | Dependency
1 | Project Initiation |  | Janna Lyn M. Rolls | 2024-01-26 | 2024-01-30 | 2024-03-11 | 100% | 32
1.1 |  | Project Charter |  | 2024-01-26 | 2024-01-26 | 2024-03-11 | 100% | 8 | Finished | Low
1.2 |  | Project Management Plan |  | 2024-01-27 | 2024-01-28 | 2024-03-11 | 100% | 8 | Finished | Medium
1.3 |  | Stakeholder Identification |  | 2024-01-27 | 2024-01-28 | 2024-03-11 | 100% | 8 | Open | Medium
1.4 |  | Task Assignment |  | 2024-01-27 | 2024-01-28 | 2024-03-11 | 100% | 8 | Finished | Low
2 | Project Planning |  | Janna Lyn M. Rolls, Lee Leighnard Jose | 2024-01-28 | 2024-01-28 | 2024-03-11 | 100% | 24
2.1 |  | System Architecture Design |  | 2024-01-28 | 2024-01-28 | 2024-03-11 | 100% | 8 | Open | High
2.2 |  | Feasibility Study |  | 2024-01-28 | 2024-01-28 | 2024-03-11 | 100% | 8 | Open | High
2.3 |  | Project Planning |  | 2024-01-29 | 2024-01-29 | 2024-03-11 | 100% | 8 | Open | High
2.4 |  | Finished Planning |  | 2024-01-29 | 2024-01-29 | 2024-03-11 | 100% | 0 | Open | High
3 | Requirement Analysis |  | Braian Robles, Lee Leighnard Jose, Yzer Vincent De Omana | 2024-01-30 | 2024-01-31 | 2024-03-11 | 100% | 24
3.1 |  | Requirements Gathering |  | 2024-01-30 | 2024-01-31 | 2024-03-11 | 100% | 8 | Open | Medium
3.2 |  | Security Planning |  | 2024-01-30 | 2024-01-31 | 2024-03-11 | 100% | 8 | Open | Medium
3.3 |  | System Security Analysis |  | 2024-01-30 | 2024-01-31 | 2024-03-11 | 100% | 8 | Open | Medium
3.4 |  | Finished Analysis |  | 2024-01-31 | 2024-01-31 | 2024-03-11 | 100% | 0 | Open | Medium
4 | System Design |  | Lee Leighnard Jose, Yzer Vincent De Omana, Janna Lyn M. Rolls, Jomarie Del Rosario | 2024-02-01 | 2024-02-01 | 2024-03-11 | 0% | 24
4.1 |  | High-Level Design |  | 2024-02-02 | 2024-02-03 | 2024-03-11 | 0% | 8 | Open | Medium
4.2 |  | Detailed Design |  | 2024-02-03 | 2024-02-03 | 2024-03-11 | 0% | 8 | Open | Medium
4.3 |  | System Specification |  | 2024-02-04 | 2024-02-04 | 2024-03-11 | 0% | 8 | Open | Low
4.4 |  | Finished System Design |  | 2024-02-07 | 2024-02-10 | 2024-03-11 | 0% | 0 | Open | Medium
5 | System Development |  | Lee Leighnard Jose, Yzer Vincent De Omana, Aldrin Fechalin | 2024-02-08 | 2024-02-08 | 2024-03-11 | 0% | 72
5.1 |  | Building/Development |  | 2024-02-09 | 2024-02-10 | 2024-03-11 | 0% | 16 | Open | High
5.2 |  | Integration Planning |  | 2024-02-10 | 2024-02-10 | 2024-03-11 | 0% | 8 | Open | High
5.3 |  | Documentation |  | 2024-02-11 | 2024-02-11 | 2024-03-11 | 0% | 8 | Open | High
5.4 |  | Test Planning |  | 2024-02-12 | 2024-02-12 | 2024-03-11 | 0% | 8 | Open | High
5.5 |  | Deployment Planning |  | 2024-02-13 | 2024-02-15 | 2024-03-11 | 0% | 8 | Open | High
5.6 |  | Training Planning |  | 2024-02-17 | 2024-02-17 | 2024-03-11 | 0% | 8 | Open | High
5.7 |  | Business Continuity Planning |  | 2024-02-19 | 2024-02-19 | 2024-03-11 | 0% | 8 | Open | High
5.8 |  | Transition Planning |  | 2024-02-21 | 2024-02-21 | 2024-03-11 | 0% | 8 | Open | High
5.9 |  | System Development Finished |  | 2024-02-22 | 2024-02-23 | 2024-03-11 | 0% | 0 | Open | High
6 | Testing |  | Princess Diane Urbano, Edelyn Tabilisma, Markus Eugene Alop | 2024-02-22 | 2024-02-23 | 2024-03-11 | 0% | 64
6.1 |  | Unit Test |  | 2024-02-22 | 2024-02-23 | 2024-03-11 | 0% | 8 | Open | Medium
6.2 |  | Function Test |  | 2024-02-23 | 2024-02-23 | 2024-03-11 | 0% | 8 | Open | Medium
6.3 |  | Integration Test |  | 2024-02-24 | 2024-02-24 | 2024-03-11 | 0% | 32 | Open | Medium
6.4 |  | Regression Test |  | 2024-02-24 | 2024-02-24 | 2024-03-11 | 0% | 8 | Open | Medium
6.5 |  | System Test |  | 2024-02-25 | 2024-02-25 | 2024-03-11 | 0% | 8 | Open | Medium
6.6 |  | User Acceptance Test |  | 2024-02-25 | 2024-02-25 | 2024-03-11 | 0% | 0 | Open | Medium
6.7 |  | Test Finished |  | 2024-02-28 | 2024-02-29 | 2024-03-11 | 0% | 40 | Open | Medium
7 | Deployment |  | Brian Villanueva, Xanthei Iona Pilares | 2024-03-01 | 2024-03-02 | 2024-03-11 | 0% | 8
7.1 |  | Deployment |  | 2024-03-02 | 2024-03-02 | 2024-03-11 | 0% | 8 | Open | High
7.2 |  | Training |  | 2024-03-03 | 2024-03-04 | 2024-03-11 | 0% | 8 | Open | High
7.3 |  | Support |  | 2024-03-04 | 2024-03-05 | 2024-03-11 | 0% | 8 | Open | High
7.4 |  | Rollout Strategy |  | 2024-03-05 | 2024-03-05 | 2024-03-11 | 0% | 8 | Open | High
7.5 |  | Development/Implementation Completed |  | 2024-03-07 | 2024-03-11 | 2024-03-11 | 0% | 0 | Open | High
8 | Operations and Maintenance |  | Lee Leighnard Jose | 2024-03-08 | 2024-03-09 | 2024-03-11 | 0% | 24
8.1 |  | Operations Activities |  | 2024-03-09 | 2024-03-09 | 2024-03-11 | 0% | 8 | Open | Medium
8.2 |  | Maintenance Activities |  | 2024-03-10 | 2024-03-11 | 2024-03-11 | 0% | 8 | Open | Medium
8.3 |  | Operations & Maintenance Completed |  | 2024-03-10 | 2024-03-11 | 2024-03-11 | 0% | 8 | Open | Medium
9 | Project Closure |  | Group | 2024-03-11 | 2024-03-11 | 2024-03-11 | 0% | 24
9.1 |  | Evaluation |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 0% | 8 | Open | Medium
9.2 |  | Final Documentation |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 0% | 8 | Open | Medium
9.3 |  | Handover Support |  | 2024-03-11 | 2024-03-11 | 2024-03-11 | 0% | 8 | Open | Medium